{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["校车预约管理系统","项目实施进度甘特图"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"校车预约管理系统","index":0,"n_rows":22,"n_cols":26,"rows_kept":22,"cut":false,"hidden":false,"merged":[[1,0,4,0],[6,0,16,0],[1,1,2,1],[3,1,4,1],[6,1,7,1],[8,1,14,1],[8,2,14,2],[6,3,7,3],[15,3,21,3]]}
["系统","一级模块","二级模块","三级模块","描述","UI设计人员","设计天数","状态","计划开始时间","完成时间","分隔","前端开发人员","开发天数","计划开始时间","完成时间","状态","后端开发人员","开发天数","计划开始时间","完成时间","状态","测试人员","测试天数","计划开始时间","完成时间","状态"]
[null,"郭班长/后勤","首页","/","去除已超时","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,"工单管理","/","维修中、待处理可关单，增加待确认状态订单，并将待确认更为待支付","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",3,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,"维修师傅端","首页","/","去除已超时","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,"工单管理",null,"去除已超时","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,"接单设置",null,"师傅下班后可处理上班前系统派的订单","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",2,null,null,"未开始","李荣","/",null,null,"未开始"]
["管理端",null,"首页","汇总数据","汇总中待确认改为“待支付”，去掉已超时","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[{"$nulls":4},"师傅详情只考核工单数和好评数","罗伟","/","未开始",null,null,"/","甘昱新","/",null,null,"未开始","夏文涛",1,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,"/","工单管理","导出","按照给的字段修改导出表单","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",2,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,null,"汇总数据","相加","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",1,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,null,"待支付","增加待支付状态订单（原先为待确认）","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",2,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,null,"待处理","增加关单按钮","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,null,"维修中","增加关单按钮","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,null,"待审核","任何情况派单时不受工种线上线下师傅限制","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",2,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,null,"详情","详情中增加维修费用，点击费用可查看使用耗材详情（小程序有）","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",1,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,"/","员工管理","/","取消考核时间","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,"/","支付成功订单",null,"增加字段区域+详细地址","罗伟","/","未开始",null,null,"/","华志杰","/",null,null,"未开始","夏文涛",0.5,null,null,"未开始","李荣","/",null,null,"未开始"]
[null,null,"接单设置",null,"师傅下班后可处理上班前系统派的订单",{"$nulls":12},2]
[null,"部署","/",null,"线上部署","/","/","/",null,"/","/","/","/",null,"/","未开始","夏文涛",0.5,null,null,"/","李荣","/",null,null,"/"]
[null,"测试小程序","/",null,"测试环境测试，回归测试，生产环境测试","/","/","/",null,"/","/","/","/",null,"/","/","/","/",null,"/","/","李荣",null,null,"/","/"]
[null,"测试管理端","/",null,"测试环境测试，回归测试，生产环境测试","/","/","/",null,"/","/","/","/",null,"/","/","/","/",null,"/","/","李荣",null,null,"/","/"]
[null,"总计",{"$f":"G22+M22+R22+W22","v":0},null,"/","/",null,"/",null,"/","/","/",null,null,"/","/","/",null,null,"/","/","/",null,null,"/","/"]

{"sheet":"项目实施进度甘特图","index":1,"n_rows":14,"n_cols":62,"rows_kept":14,"cut":false,"hidden":false,"merged":[[0,0,0,1],[1,0,12,0],[1,1,2,1],[4,1,6,1],[7,1,11,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,2,8],[1,9,2,9],[1,10,2,10],[1,11,2,11],[1,12,2,12],[1,13,2,13],[1,14,2,14],[1,15,2,15],[1,16,2,16],[1,17,2,17],[1,18,2,18],[1,19,2,19],[1,20,2,20],[1,21,2,21],[1,22,2,22],[1,23,2,23],[1,24,2,24],[1,25,2,25],[1,26,2,26],[1,27,2,27],[1,28,2,28],[1,29,2,29],[1,30,2,30],[1,31,2,31],[1,32,2,32],[1,33,2,33],[1,34,2,34],[1,35,2,35],[1,36,2,36],[1,37,2,37],[1,38,2,38],[1,39,2,39],[1,40,2,40],[1,41,2,41],[1,42,2,42],[1,43,2,43],[1,44,2,44],[1,45,2,45],[1,46,2,46],[1,47,2,47],[1,48,2,48],[1,49,2,49],[1,50,2,50],[1,51,2,51],[1,52,2,52],[1,53,2,53],[1,54,2,54],[1,55,2,55],[1,56,2,56],[1,57,2,57],[1,58,2,58],[1,59,2,59],[1,60,2,60],[1,61,2,61]]}
["              时间                内容",null,null,"2023-07-05","2023-07-06","2023-07-07","2023-07-08","2023-07-09","2023-07-10","2023-07-11","2023-07-12","2023-07-13","2023-07-14","2023-07-15","2023-07-16","2023-07-17","2023-07-18","2023-07-19","2023-07-20","2023-07-21","2023-07-22","2023-07-23","2023-07-24","2023-07-25","2023-07-26","2023-07-27","2023-07-28","2023-07-29","2023-07-30","2023-07-31","2023-08-01","2023-08-02","2023-08-03","2023-08-04","2023-08-05","2023-08-06","2023-08-07","2023-08-08","2023-08-09","2023-08-10","2023-08-11","2023-08-12","2023-08-13","2023-08-14","2023-08-15","2023-08-16","2023-08-17","2023-08-18","2023-08-19","2023-08-20","2023-08-21","2023-08-22","2023-08-23","2023-08-24","2023-08-25","2023-08-26","2023-08-27","2023-08-28","2023-08-29","2023-08-30","2023-08-31","2023-09-01"]
["南交报修系统","产品","产品文档编写",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[]
[null,"UI","ui设计",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,"开发","管理端",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"小程序",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"后端",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,"测试","小程序",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"管理端",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"测试环境测试",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"回归测试",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"生产环境测试",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,"部署","线上部署",null,null,null,"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末",{"$nulls":5},"周末","周末"]
[null,null,"注："]